## _Project Plan_Notes
WxC Generic Calling Plan
Project Plan over all
Planning
Project Review and kick-off
Discovery and Design Planning
Phone model review and verification
CUBE interop design
UCM review
3rd party integrations review
Webex Control Hub Provisioning
Tenant spin up and licensing
Azure AD Setup
Verify domain ownership
Configure Directory Integration (Directory connector or Azure)
Configure Single Sign on
CCUC Setup
PSTN Provisioning (UCaaS)
WxC trunk creation
Customer Provided certificate
RR SBC configuration
Porting LOA completed and signed by customer
WxC Configuration
Migration utility spin up and integration
Template creation and review
Location configuration
User configuration
Feature Configuration (auto attendants, hunt lists, call queues)
Dial plan
3rd party integrations
Redsky Provisioning
Setup SSO
Configure buildings and locations
Configure location tracking
Configure notification recipients
Pilot
Device migration
Phone UAT
Cutover (Phase x)
Device registration
Dial plan updates
Users/numbers/features WxC bulk update
3rd party interop updates
PSTN Porting
Documentation MS handoff
Acceptance/Closure