## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
xPTFMosZKEKFeE4Zdm6uvWQAB24- | UCM Integration | Red River | Not started | Important |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/3 | Investigate Existing Dial Plan;Test Calling;Update Dial Plan | High Priority | Setup UCM integration 1. Partitions 2. CSSs 3. Trunks 4. Route patterns
-XxmmGs1mEClurawcEu_EGQAMPhx | RedSky E911 | High Level Tasks | Not started | Medium |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/1 | RedSky Workbook | Medium Priority | Discuss RedSky E911
NmRCS7FA5E2odrDmwIfMemQAIhOC | Configure Cloud Connected UC | Red River | Not started | Medium |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/3 | Enable Features;Setup CCUC;Activate CCUC | Low Priority | Setup CCUC https://help.webex.com/en-us/article/jv0u1db/Webex-Cloud-Connected-UC-Overview
oCcciBjDUUa3sv6K4VKRH2QACEkb | Phase X - Cutover | Cutover(s) | Not started | Important |  | Sam Palatucci | 07/03/2025 |  | 07/31/2036 | false | false |  |  | 0/3 | Support;Prepare;Cutover |  | Phase X cutover Sites: Site 1
QhkcHmRcTk-zgAZEsrlB_mQABmQO | Configure Locations | Red River | Not started | Important |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/1 | Configure Locations | High Priority | Configure Webex Calling locations
3zx4fsf6x06Ch-BmV7oKEWQAIRHd | Webex SAML SSO Authentication | Red River | Not started | Important |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/2 | Determine SAML SSO IdP;Configure SAML SSO | High Priority | Configure Webex SAML SSO authentication https://help.webex.com/en-us/article/lfu88u/Single-Sign-On-Integration-in-Control-Hub
USR6-w37AUSYdcU8w-X1ZWQAHObW | Webex Directory Integration | Red River | Not started | Important |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/2 | Determine Directory Integration Type;Configure Directory Integration | High Priority | Configure directory integration https://help.webex.com/en-us/article/nj34yk2/Ways-to-add-users-to-your-Control-Hub-organization
vdg2ztH7gkyvhJAcRIsrn2QAN5_E | Webex Domain Management | Red River | Not started | Important |  | Sam Palatucci | 07/03/2025 |  |  | false | false |  |  | 0/2 | Domains Claimed;Domains Verified | High Priority | Configure domains in Control Hub https://help.webex.com/en-us/article/cd6d84/Manage-your-domains
6UMm7onDwkyOKXfB8d2352QAOhsj | Local Gateway(s) Integration | Red River | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/2 | Configure CUBE X;Backup Configs | High Priority | Setup Local Gateway(s) https://help.webex.com/en-us/article/t9xctu/Get-started-with-Local-Gateway 1. Upgrade firmware 2. Certificates 3. Configuration 4. Testing
w-djOlCQVkuMmIsISkcyRGQAOL8C | Discovery | High Level Tasks | Not started | Medium |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/3 | UC Applications;Webex Control Hub;3rd Party Integrations | Medium Priority | Discovery of existing environment
GDSFnpxZB0WGsxQgU0Na5WQADSH7 | Setup Red River Access | Customer | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/4 | Webex Control Hub;O365/Domain Account;VPN Requirements;UC Applications | High Priority | Environment Access
g9s35zYylkqS3TB9I8PA0mQALS1p | Migration Planning | High Level Tasks | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/3 | Site Dependencies;Phases;Webex Calling Workbook | High Priority | Discuss migration strategy
S2gZcrQFUU-HfHnolcRZRmQAJoyg | Number Porting | High Level Tasks | Not started | Medium |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/3 | Porting/FOC Date;LOA Document;Acquire CSR | Low Priority | Discuss porting process
I1ex3fWSDkSwRVxrbXnFUWQABPxG | Cloud Connected UC | High Level Tasks | Not started | Medium |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/3 | UC Version Requirements;Optional Features;Expressway MRA | Low Priority | Discuss CCUC Integration
EGgoxEOc50aq1Kq4GUa-LWQAM7oK | IP Phone Migration | High Level Tasks | Not started | Medium |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/2 | Compatibility Requirements;Firmware Requirements | High Priority | Migration: https://www.cisco.com/c/en/us/products/collateral/collaboration-endpoints/unified-ip-phone-7800-series/guide-c07-742786.html https://upgrade.cisco.com/e2m_converter_wxc#execute
nRqBFUGPNEqRl5Nn8QjtnmQALO_R | Firewall Requirements | High Level Tasks | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/1 | Webex Calling Firewall Workbook | High Priority | IP addresses, NATs, ports and proxy requirements
QmaKNcDyBk6PhlpUOvQLRmQAIA-D | Configure RedSky E911 | Red River | Not started | Medium |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/2 | Configure RedSky;Setup SAML SSO | Medium Priority | Setup RedSky E911
m2d03Hs-_UylXgxxHBd2IWQAETOR | Webex Calling Features | High Level Tasks | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/4 | Survivability;PSTN;Paging;3rd Party Integrations | High Priority | Webex Calling feature details
Zl1tjb2A_E6P1fOKY3k5YWQAM4FO | Webex Control Hub Setup | High Level Tasks | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/4 | Subscription;Domains;Authentication;Directory Integration | High Priority | Webex Control Hub baseline setup
6RUewZ20JEuQvTPJQNUJemQAOmrN | CUBE(s) Requirements | High Level Tasks | Not started | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false |  |  | 0/3 | Model/Firmware;Certificates;Trunking Type | High Priority | Requirements for CUBE(s) to connect to Webex Calling via trunks
NC67iQida0qMFEtqEl-3RWQABa_5 | RFC 1: Description (CHGXXXXXX) | RFC(s) | Completed | Important |  | Sam Palatucci | 07/02/2025 |  |  | false | false | 07/02/2025 | Sam Palatucci | 0/3 | Submited;Approved;Completed | High Priority

## Plan name
Plan name | Tracker
Plan ID | YKVRr1wZv0uCmX6XHsBu_WQAHVe2
Date of export | 07/08/2025